## Sheet1 (hidden)
Phase | Checklist Task
Stakeholder Management | Identify all stakeholder groups (Finance, Development, Programs, HR, IT, Board, Audit/Compliance, etc.)
Stakeholder Management | Map stakeholders by influence vs. impact (decision power vs. most affected)
Stakeholder Management | Define each group’s needs (e.g., Development → donor reporting; Programs → outcome dashboards)
Communication Plan | Create a communication plan (who needs updates, how often, in what format)
Communication Plan | Set up recurring stakeholder check-ins (steering committees, working groups)
Communication Plan | Translate system updates into mission-related terms (e.g., time saved → more program delivery)
Requirements Gathering | Run cross-department workshops to capture must-haves and nice-to-haves
Requirements Gathering | Validate requirements with end-users (not just leadership)
Requirements Gathering | Include program and development staff in reporting/dashboard needs
Transparency & Buy-In | Share selection criteria openly (functionality, cost, compliance, scalability)
Transparency & Buy-In | Provide side-by-side comparisons of systems with nonprofit-specific features
Transparency & Buy-In | Invite feedback loops before final recommendation (surveys, voting)
Change Readiness & Risk Mitigation | Assess organizational readiness for change (culture, capacity, skills)
Change Readiness & Risk Mitigation | Anticipate resistance — document likely pushbacks and responses
Change Readiness & Risk Mitigation | Build a quick-win roadmap (early improvements to show value fast)
Training & Adoption | Identify training needs by role (executive dashboards vs. transactional users)
Training & Adoption | Develop role-specific training
Training & Adoption | Create champions/super-users in each department to model adoption
Training & Adoption | Determeine training needs - who, when, how
Training & Adoption | Setup training sessions, workshops, office hours
Training & Adoption | Record trainings, send FAQs, supproting materials
Ongoing Support & Continuous Feedback | Establish post-selection support structure (help desk, office hours)
Ongoing Support & Continuous Feedback | Gather feedback after rollout through surveys and focus groups
Ongoing Support & Continuous Feedback | Adjust processes or dashboards based on user input

## Instructions
#VALUE!
This checklist outlines the 7 phases of system implementation change management. Each phase contains key actions to help guide your organization through a successful transition.
Review each phase in order — check off items once they are completed and use the Dashboard to track progress.
Assign an Owner for each action to ensure accountability.
If your team would like tailored support in navigating these phases, reach out to Lisa Toback at Ltoback@kiwipartners.com or Kate Koraia at Kkoraia@kiwipartners.com
Kiwi Partners' Consulting team specialize in helping nonprofits reduce risk, drive adoption, and achieve impact with their finance systems.

## Change Management Checklist
#VALUE!
Organization Name:
Project Name:
Change Management Checklist
Phase | Key Actions | Owner / Responsible | Checkpoint / Deliverable | Complete
1. Stakeholder Management
| Identify all stakeholder groups (Finance, Dev, Programs, HR, IT, Board, Compliance, Selection Committee) | Project Manager | Stakeholder list completed | FALSE
| Map stakeholders by influence vs. impact | PM + Leadership | Stakeholder matrix approved | FALSE
| Define each group’s needs | Department Leads | Needs documented - communication, training plan | FALSE
| Assess stakeholder change readiness | Change Lead/PM | Readiness survey completed | FALSE
| Assign stakeholder champions. (Note: The Stakeholder champion is the main point of contact to reach out for any conflicts ) | Department Heads | Champions designated | FALSE
2. Communication Plan
| Create communication plan (who, how often, format) | PM + Comms Lead + Leadership | Plan approved | FALSE
| Set up recurring check-ins (steering committee, working groups) | PM | Calendar scheduled | FALSE
| Share early success stories | PM/Leadership | Monthly update issued | FALSE
| Reach out to involved departments for continuous project feedback | Comms Lead/PM | Feedback engagement tracked | FALSE
| Enable two-way communication | Comms Lead | Develop communication channels (Team's chat groups, slack, etc. for project specific discussion) | FALSE
| Provide weekly project updates (Status reports) to provide milestone updates, project timeline updates, etc | Comms Lead | Weekly Status Reports | FALSE
3. Requirements Gathering
| Run cross-department workshops | Business Analyst | Workshops conducted | FALSE
| Validate requirements with end-users | Business Analyst | Requirements approved | FALSE
| Capture current pain points | Business Analyst |  | FALSE
| Create central repository for requirements | Business Analyst |  | FALSE
| Include reporting/dashboard needs | Program & Dev Leads | User stories documented | FALSE
| Outline priorities and identify short, medium, long term plans to address needs | PM + Stakeholders | Prioritization matrix with Short, medium and long-term goals | FALSE
4. Transparency & Buy-In
| Share system selection criteria openly | PM | Criteria distributed | FALSE
| Provide side-by-side system comparisons | PM | Comparison shared | FALSE
| Invite feedback loops before final recommendation | Comms Lead | Survey results analyzed | FALSE
| Communicate alignment with mission | Leadership | Messaging approved | FALSE
| Communication from Leadership once a system is selected | Leadership | Email related to the system selection process, selected software and anticipated go-live | FALSE
| Send email to larger team when major milestones are hit (i.e new Chart of Accounts have been developed, etc.) | Leadership | Email to larger team including milestone and the positive impact it will have on the team | FALSE
5. Change Readiness & Risk Mitigation
| Confirm with key team members readiness for a system implementation. Things to consider: Month end- closes, black-out dates, concurrent projects and/or audits | Change Lead | Readiness report completed | FALSE
| Anticipate resistance & document responses | Change Lead | Resistance log created | FALSE
| Build quick-win roadmap | PM | Quick-win roadmap approved | FALSE
| Conduct risk assessment | PM + IT | Risk register completed | FALSE
| Develop mitigation and conversion plan | PM | Mitigation strategies documented | FALSE
| Monitor employee sentiment | Change Lead | Survey results tracked | FALSE
| Align system adoption with workflows | Business Analyst | Workflow mapping completed | FALSE
6. Training & Adoption
| Identify role-based training needs | Training Lead | Training matrix completed | FALSE
| Develop role-specific content | Training Lead | Content approved | FALSE
| Create champions/super-users | Department Heads | Champions trained | FALSE
| Determine training schedule (who, when, how) | Training Lead | Training calendar ready | FALSE
| Conduct sessions, workshops, office hours | Training Lead | Training sessions completed | FALSE
| Record trainings & distribute supporting materials | Training Lead | Resources shared | FALSE
| Encourage hands-on practice | Training Lead | Practice sessions tracked | FALSE
| Offer refresher & microlearning sessions | Training Lead | Participation logged | FALSE
| Track adoption metrics | PM + Change Lead | Adoption metrics reported | FALSE
7. Ongoing Support & Continuous Feedback
| Establish post-rollout support (help desk, office hours) | IT/Support | Support structure live | FALSE
| Gather post-rollout feedback | Change Lead | Surveys/focus groups completed | FALSE
| Adjust processes/dashboards based on input | PM + Dept Leads | Updates implemented | FALSE
| Maintain continuous improvement loop | PM + Change Lead | Improvement cycle ongoing | FALSE
| Recognize early adopters | Leadership | Recognition program active | FALSE
| Share usage metrics & success stories | PM + Comms Lead | Metrics dashboard shared | FALSE
| Plan for future updates/integrations | PM + IT | Future roadmap approved | FALSE
Legend Owner/Responsible
Short Form | Long Form
PM | Project Manager
Comms Lead | Communication Lead
Tech Lead | Technical Lead
BA | Business Analyst
Ops Lead | Operations Lead
Finance Lead | Financial Lead
Legal | Legal Representative
Risk Lead | Risk Management Lead
Change Lead | Change Management Lead
Training Lead | Training Coordinator/Lead
Support Lead | Support Services Lead
IT | Information Technology Lead
Dept | Department Lead
Program and Dev | Program and Development Leads

## Dashboard
Phase | Total Tasks | Completed Tasks | Progress (%)
1. Stakeholder Management | 5 | 0 | 0%
2. Communication Plan | 6 | 0 | 0%
3. Requirements Gathering | 6 | 0 | 0%
4. Transparency & Buy-In | 6 | 0 | 0%
5. Change Readiness & Risk Mitigation | 7 | 0 | 0%
6. Training & Adoption | 9 | 0 | 0%
7. Ongoing Support & Continuous Feedback | 7 | 0 | 0%