## Instructions
#VALUE!
Welcome! This workbook outlines a high-level ERP implementation plan tailored for nonprofit organizations. Here's how to use this first tab "ERP Implementation Workplan":
7 Phases of ERP Implementation: Each row represents a major task in the in the project phases. Estimated Timeline: Enter start and end dates for each phase to guide scheduling and planning.
If your team would like tailored support in navigating your ERP implementation, reach out to Lisa Toback, Ltoback@kiwipartners.com or Kate Koraia at kkoraia@kiwipartners.com
Nonprofits we’ve supported report time savings, improved data accuracy, and better support for organizational growth. With the right implementation partner, transitions can be smoother, with better adoption, and more impact.
Whether you’re just exploring options or ready to make a change, we’re here to help. Contact us for a free consultation.

## ERP Implementation Workplan
#VALUE!
Task | Timeline
ERP Implementation – High-Level Workplan
Phase 1: Discovery & Planning | Weeks 1-2
Conduct project kickoff and align on objectives
Define scope, timeline, and key milestones
Determine stakeholders, influence and impact
Establish communication structure
Develop Change Management Plan
Collect and review existing financial processes and data
Phase 2: Design & Preparation | Weeks 3-6
Define reporting and dimensional requirements
Align on Chart of Accounts structure and key financial dimensions
Identify integrations with other systems (e.g., AP automation, expense management)
Develop data migration strategy (conversion methodology)
Phase 3: Build & Validation | Weeks 7-10
Set up core entities, dimensions, and financial reporting framework
Prepare test scenarios for financial processes
Conduct initial data migration test and validate results
Review draft reports and dashboards with client team
Phase 4: Training & User Readiness | Weeks 11-12
Provide role-based training for finance team and key users
Conduct hands-on practice sessions (first bank reconciliation, first journal entry etc.)
Finalize user access and roles
Confirm readiness for go-live through a cutover checklist
Phase 5: Go-Live & Transition | Weeks 13-16
Execute final data migration and validate the migration
Transition to the new system and begin live processing
Monitor transactions and reports for accuracy
Provide additional training and support during the first month
Phase 6: Post Go-Live Optimization | Weeks 17-18
Conduct troubleshooting sessions
Deliver post-go-live enhancements (reports, dashboards, workflows)
Gather feedback from users and refine processes
Transition to support model
Phase 7: Project Management | Weeks 1-18
Weekly Status Memos/communication to stakeholders
Assess, monitor and migate risk
Incorporate Change Management tasks into workplan
Monitor scope and timing

## Comments
Add Comments if needed to clarify dependencies, risks, or key decisions.